## Large Scale
Sections of Project	Priority	Done?			Not started
Rhythm	1	WIP			WIP
Cutscenes	5	Not started			Complete
Menus	5	Not started
Beat 'em up	13	Not started
Dodging	13	Not started
Boss Fight	21	Not started

## Rhythm
Sections of Project	Priority	Done?
Code	1	WIP
Music	5	WIP
Art	8	WIP
Level Design	21	WIP

Code
Task	Priority	Time	Done?
Make Game Playable	1	21	WIP
Play Audio	8	2	Complete
Engine to Store Levels	13	3	Complete
Others	13	5	Not started

Music
Task	Priority	Time	Done?
Write	1	5	Complete
Record	5	5	WIP
Integrate with Plot	21	13	Not started

Art
Task	Priority	Time	Done?
Gameplay Elements	1	1	Complete
Character Art	3	2	WIP
Backgrounds	3	?	Not started
Animation	13	?	Not started

Level Design
Task	Priority	Time	Done?
Stats	1	1	Not started
Combat System	3	2	Not started
Spells	5	2	Not started
Enemies	8	1	Not started
Levelling Up	13	1	Not started
Testing (Iterate previous)	21	13	WIP
Level Editor	21	21	WIP